## Sheet1
ID | Task Name | Duration (day) | Start Date | End Date
1 | Semester 1 | 104 | 2022-08-19 | 2022-12-01
2 | Initiating | 6 | 2022-08-19 | 2022-08-25
3 | Project allocation | 1 | 2022-08-25 | 2022-08-25
4 | Background study | 21 | 2022-08-25 | 2022-09-15
5 | Read and compare the related work | 21 | 2022-08-25 | 2022-09-15
6 | Project proposal & ethic form submission | 1 | 2022-09-08 | 2022-09-08
7 | Design | 7 | 2022-09-15 | 2022-09-22
8 | Design system architecture | 3 | 2022-09-15 | 2022-09-18
9 | Design database | 4 | 2022-09-18 | 2022-09-22
10 | Implementation | 105 | 2022-09-22 | 2023-01-05
11 | Implement database | 3 | 2022-09-22 | 2022-09-25
12 | Build basic structure of this web site (front end & back end) | 4 | 2022-09-25 | 2022-09-29
13 | Develop a webpage for inputing questions, solutions and distractors, and variants | 7 | 2022-09-29 | 2022-10-06
14 | Develop a function to generate Parsons problems | 14 | 2022-10-06 | 2022-10-20
15 | Develop a webpage for students to filter the scope of Parsons problems | 7 | 2022-10-20 | 2022-10-27
16 | Develop a webpage for students to solve Parsons problems | 28 | 2022-10-27 | 2022-11-24
17 | Develop a function to evaluate students' solution and give feedback | 7 | 2022-11-24 | 2022-12-01
18 | Gantt chart submission | 1 | 2022-09-29 | 2022-09-29
19 | Report writing | 133 | 2022-08-25 | 2023-01-05
20 | Progress report submission | 1 | 2022-11-10 | 2022-11-10
21 | Progress presentation | 1 | 2022-11-17 | 2022-11-17
22 | Semester 2 | 113 | 2023-01-05 | 2023-04-28
23 | Implementation | 49 | 2023-01-05 | 2023-02-23
24 | Develop a function to evaluate students' solution and give feedback | 12 | 2023-01-05 | 2023-01-17
25 | Develop a webpage to show statistical analysis of mastery degree of students | 10 | 2023-01-30 | 2023-02-09
26 | Implementation mostly done | 1 | 2023-02-23 | 2023-02-23
27 | Testing | 10 | 2023-02-13 | 2023-02-23
28 | User Acceptance Test | 10 | 2023-02-13 | 2023-02-23
29 | Report writing | 14 | 2023-02-23 | 2023-03-09
30 | Poster submission | 1 | 2023-03-23 | 2023-03-23
31 | Closing | 1 | 2023-04-13 | 2023-04-13
32 | Final presentation (demo video) | 1 | 2023-04-13 | 2023-04-13
33 | Poster session | 1 | 2023-04-13 | 2023-04-13
34 | Final report submission | 1 | 2023-04-13 | 2023-04-13

## Sheet2
Priority | Risk identifier and Description
1 | Risk 1: The computer used for implementation may break down
2 | Risk 3: Users reject this website because of the inferior user interface
3 | Risk 2: The system does not support different devices
Notes: Priority 1 is the highest risk